## FMZINp1_grafiks_regulējuma_apst
1. pielikums Informatīvajam ziņojumam par Eiropas Savienības fondu un Atveseļošanas fonda plāna ieviešanu 2025. gada novembrī-decembrī
ES fondu 2021.–2027. gada plānošanas perioda MK noteikumu par specifisko atbalsta mērķu ieviešanu izstrādes grafiks regulējuma apstiprināšanai ****
Sagatavots 16.12.2025 | [8 empty] | PLĀNOTAIS FINANSĒJUMS
PM Nr. | Prior. Nr. | Prioritātes nosaukums | SAM Nr. | SAM nosaukums | Pasākuma Nr. | Pasākuma nosaukums | Kārtas Nr. | Fonds | ES FONDU finansējums (ieskaitot elastības finansējumu)* | KOPĀ (ar nac. līdzfinansējumu +15%**) | NACIONĀLAIS līdzfinansējums | Atbildīgā iestāde | Izskatīšanas AK datums/ plānotais gads un ceturksnis*** | Izskatīšanas UK datums/ pānotais gads un ceturksnis*** | TAP saskaņošanas uzsākšanas datums/ plānotais gads un ceturksnis | RISKA LĪMENIS | MK apstiprināšanas plānotais gads un ceturksnis/apstiprināšanas datums | Atlases uzsākšanas datums/ plānotais gads un ceturksnis****
1 | 2 |  | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 15 | 16
KAVĒTA NORMATĪVĀ REGULĒJUMA IZSTRĀDE - un potenciāli plānota finansējuma pārdale citiem mēŗkiem |  |  |  |  | 7: Kopā:; 8: 11298293; 9: 13292110; 10: 1993817
2 | 2.2. | Vides aizsardzība un attīstība | 2.2.2. | “Pārejas uz aprites ekonomiku veicināšana” | 2.2.2.3. | Notekūdeņu dūņu pārstrāde***** | _ | KF | 0 | 0 | 0 | KEM | 2025 II | 2025 II | 2025-06-11 | KAVĒTS | 2025 II | 2025 IV
3 | 3.1. | Ilgtspējīga TEN-T infrastruktūra | 3.1.1. | “Attīstīt ilgtspējīgu, pret klimatu izturīgu, inteliģentu, drošu un vairākveidu TEN-T infrastruktūru” | 3.1.1.7. | Iekšzemes intermodālo termināļu ("sauso ostu") attīstības projekti***** | _ | KF | 11298293 | 13292110 | 1993817 | SM | Plānots izskatīt AK 27.03.2025 (atsaukts 19.03.2025.) | 2025 II | 2025 II | KAVĒTS | 2025 II | 2025 IV
NORMATĪVAIS REGULĒJUMS IZSTRĀDĒ |  |  |  |  | 7: Kopā; 8: 155230017; 9: 182623553; 10: 27393536
1 | 1.5. | Investīciju fonds uzņēmējdarbības attīstībai | 1.5.1. | "Ieguldījumi uzņēmējdarbībā, kas atbalsta STEP mērķu sasniegšanu" | 1.5.1.0 | "Ieguldījumi uzņēmējdarbībā, kas atbalsta STEP mērķu sasniegšanu" | _ | ERAF | 34000000 | 40000000 | 6000000 | EM | N/A, jo FI | N/A, jo FI | 2025-11-10 | IZSTRĀDĒ | 2025 IV | 2026 I
2 | 2.1. | Klimata pārmaiņu mazināšana un pielāgošanās klimata pārmaiņām | 2.1.1. | “Energoefektivitātes veicināšana un siltumnīcefekta gāzu emisiju samazināšana” | 2.1.1.6. | Pašvaldību ēku energoefektivitātes paaugstināšana | 3 | ERAF | 16464931 | 19370508 | 2905577 | VARAM | 2026 I | 2026 II | 2025-11-21 | IZSTRĀDĒ | 2026 II | 2026 III
2 | 2.1. | Klimata pārmaiņu mazināšana un pielāgošanās klimata pārmaiņām | 2.1.3. | “Veicināt pielāgošanos klimata pārmaiņām, risku novēršanu un noturību pret katastrofām” | 2.1.3.1. | Pašvaldību pielāgošanās klimata pārmaiņām | 2 | ERAF | 9264007 | 10898832 | 1634825 | VARAM | 2023-09-28 | 2026 I | 2025-10-03 | IZSTRĀDĒ | 2026 II | 2026 III
2 | 2.6. | Enerģētiskās neatkarība stipirnāšana | 2.6.1. | "Veicināt enerģijas starpsavienojumu un saistītās pārvades, sadales, uzglabāšanas un atbalsta infrastruktūras izbūvi, kā arī kritiskās enerģētikas infrastruktūras aizsardzību un uzlādes infrastruktūras izvēršanu" | 2.6.1.1. (2.1.2. 2.k.) | “Atjaunojamo energoresursu enerģijas veicināšana - biometāns” | _ | ERAF | 4000000 | 4705883 | 705883 | KEM | IPIA izņēmums (UK lēm. 09.06.2025.) | IPIA izņēmums (UK lēm. 09.06.2025.) | 2025-10-13 | IZSTRĀDĒ | 2025 IV | 2026 I
3 | 2.6. | Enerģētiskās neatkarība stipirnāšana | 2.6.1. | "Veicināt enerģijas starpsavienojumu un saistītās pārvades, sadales, uzglabāšanas un atbalsta infrastruktūras izbūvi, kā arī kritiskās enerģētikas infrastruktūras aizsardzību un uzlādes infrastruktūras izvēršanu" | 2.6.1.2. (2.1.4.) | Enerģētiskās drošības infrastruktūras attīstība | _ | ERAF | 31000000 | 36470589 | 5470589 | KEM | IPIA izņēmums (UK lēm. 09.06.2025.) | IPIA izņēmums (UK lēm. 09.06.2025.) | 2025-10-14 | IZSTRĀDĒ | 2025 IV | 2026 I
4 | 4.2. | Izglītība, prasmes un mūžizglītība | 4.2.1. | “Uzlabot vienlīdzīgu piekļuvi iekļaujošiem un kvalitatīviem pakalpojumiem izglītības, mācību un mūžizglītības jomā, attīstot pieejamu infrastruktūru, tostarp, veicinot noturību izglītošanā un mācībā attālinātā un tiešsaistes režīmā” | 4.2.1.1. | Infrastruktūras izveide starpnozaru sadarbības un atbalsta sistēmas izveidei bērnu attīstībai | _ | ERAF | 3697500 | 4350000 | 652500 | VK | IPIA izņēmums (UK lēm. 09.06.2025.) | IPIA izņēmums (UK lēm. 09.06.2025.) | 2025-10-14 | IZSTRĀDĒ | 2026 I | 2026 I
4 | 4.3. | Nodarbinātība un sociālā iekļaušana | 4.3.3. | “Uzlabot visu darba meklētāju, jo īpaši jauniešu – it sevišķi, īstenojot Garantiju jauniešiem –, ilgstošo bezdarbnieku un darba tirgū nelabvēlīgā situācijā esošo grupu, un ekonomiski neaktīvo personu piekļuvi nodarbinātībai un aktivizācijas pasākumiem, kā arī veicinot pašnodarbinātību un sociālo ekonomiku” | 4.3.3.1. | Bezdarbnieku, darba meklētāju un bezdarba riskam pakļauto personu kvalifikācijas un prasmju paaugstināšana | _ | ESF | 40672500 | 47850000 | 7177500 | LM | 2024-12-19 | 2025-02-12 | 2025-07-25 | IZSTRĀDĒ | 2025 IV | 2026 I
6 | 6.1. | Pāreja uz klimatneitralitāti | 6.1.1. | "Pārejas uz klimatneitralitāti radīto ekonomisko, sociālo un vides seku mazināšana visvairāk skartajos reģionos" | 6.1.1.1. | Atteikšanās no kūdras izmantošanas enerģētikā | 4 | TPF | 2007407 | 2361656 | 354249 | VARAM | Pieteikts uz 18.decembra AK | 2025 IV | 2025-11-25 | IZSTRĀDĒ | 2025 IV | 2026 I
6 | 6.1. | Pāreja uz klimatneitralitāti | 6.1.1. | "Pārejas uz klimatneitralitāti radīto ekonomisko, sociālo un vides seku mazināšana visvairāk skartajos reģionos" | 6.1.1.1. | Atteikšanās no kūdras izmantošanas enerģētikā | 5 | TPF | 14123672 | 16616085 | 2492413 | VARAM | Pieteikts uz 18.decembra AK | 2026 II | 2025-11-25 | IZSTRĀDĒ | 2026 II | 2026 III
* ES fondu daļa, ieskaitot elastības finansējumu (50% no 2026.gada un 2027.gada finansējuma). Elastības finansējums nav pieejams atlasēm līdz Eiropas Komisijas lēmumam par Programmas ieviešanas vidusposma ziņojumu.
** Nacionālais finansējums tiek norādīts ar 15% līdzfinansējuma likmi, ņemot vērā Programmā noteikto, ka tiks nodrošināts nacionālais līdzfinansējums vismaz 15% un ES fondu finansējuma likme prioritātes līmenī būs 85%.
Atsevišķu investīciju gadījumā līdzfinansējuma likmes var atšķirties, vienlaikus nodrošinot, ka tiks ievērots Programmā noteiktais, ka ES fondu līdzfinansējums tiks nodrošināts 85% prioritātes līmenī.
*** N/A kolonnā "Iesniegšana AK 2021-2027 (gads un ceturksnis)/Izskatīšanas datums AK" un kolonnā "Iesniegšana UK 2021-2027 (gads un ceturksnis)/ UK apstiprināšanas datums" norādīts pasākumiem,
kas tiks īstenoti ar finanšu instrumentu palīdzību un šādā gadījumā nav attiecināms AK un UK process.
**** Attēlots investīciju sadalījums atbilstoši vidusposma un investīciju optimizācijas pārdaļu priekšlikumiem, attiecīgi grozījumi Eiropas Savienības kohēzijas politikas programmā 2021.–2027.gadam vēl saskaņošanā.
*****MK š.g. 25.novembra sēdē atbalstīts papildu ES fondu finansējums Latvijas Onkoloģiskā centra (LOC) infrastruktūrai no pasākumiem, kuru ieviešana kavējas (t.sk. 2.2.2.3.pasākuma "Notekūdeņu dūņu pārstrāde" 23,1 milj. EUR, un daļa no SM 3.1.1.7.pasākuma)
Finanšu ministrs | [16 empty] | A. Ašeradens
Jolanta Baldunčika, 25664854
jolanta.balduncika@fm.gov.lv

## GRAFIKI II (hidden)
KUMULATĪVI
Laika grafiks uz 25.04.2023.
MK not. gads un ceturksnis | MK noteikumu faktiskā izpilde; finansējums kumulatīvi, milj. EUR | MK noteikumu finansējums, EUR | MK noteikumu finansējums, milj. EUR - NOBĪDE kumulatīvi | Atlašu finansējums kumulatīvi, milj. EUR | Atlašu finansējums, EUR |  | MK noteikumu apstiprināšanas plāns uz 25.04.2023; finansējums kumulatīvi, milj. EUR | MK noteikumu finansējums, EUR | Atlašu finansējums kumulatīvi uz 25.04.2023., milj. EUR | Atlašu finansējums, EUR | Nobīdes MKN | Nobīdes atlases
2022 IV | 0 | 0 | #REF! | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 I | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 II | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 III | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 I | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2024 II | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2024 III | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2024 IV | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2025 I | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2025 II | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2025 III | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2025 IV | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2026 I | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
Uzsaukums par elastības finansējuma apjomu 2026.g. | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2026 II | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2026 III | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2026 IV | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2027 I | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2027 II | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2027 III | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2027 IV | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
bez TP prioritātes |  | #REF! |  |  | #REF! |  |  | #REF! |  | #REF!
|  | #REF! |  |  | #REF! |  |  | #REF! |  | #REF!
|  | #REF! |  |  | #REF! |  |  | #REF! |  | #REF!
BEZ KUMULATĀCIJAS
Laika grafiks uz 25.04.2023.
MK not. gads un ceturksnis | MK noteikumu faktiskā izpilde; finansējums , milj. EUR | MK noteikumu finansējums, EUR | MK noteikumu finansējums, milj.EUR - NOBĪDE | Atlašu finansējums, milj. EUR | Atlašu finansējums, EUR |  | MK noteikumu apstiprināšanas plāns uz 25.04.2023; finansējums kumulatīvi, milj. EUR | MK noteikumu finansējums, EUR | Atlašu finansējums kumulatīvi uz 25.04.2023., milj. EUR | Atlašu finansējums, EUR
2022 IV | 0 | 0 | 0 | 0 | 0 |  | #REF! | #REF! | #REF! | #REF!
2023 I | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2023 II | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2023 III | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2024 I | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2024 II | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2024 III | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2024 IV | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2025 I | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2025 II | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2025 III | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2025 IV | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2026 I | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
Uzsaukums par elastības finansējuma apjomu 2026.g. | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2026 II | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2026 III | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2026 IV | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2027 I | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2027 II | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2027 III | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
2027 IV | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
Kopā | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF!
KUMULATĪVI
Laika grafiks uz 25.04.2023.
| MK noteikumu finansējums pa ministrijām kumulatīvi, milj. EUR | [25 empty] | MK noteikumu finansējums pa ministrijām kumulatīvi uz 25.04.2023., milj. EUR
| SM | NOBĪDE | EM | NOBĪDE | VARAM | NOBĪDE | IZM | NOBĪDE | VM | NOBĪDE | LM | NOBĪDE | KM | NOBĪDE | FM | NOBĪDE | VK | NOBĪDE | IeM | NOBĪDE | TM | NOBĪDE | KEM | NOBĪDE | VARAM izpilde | LM izpilde |  | SM | EM | VARAM | IZM | VM | LM | KM | FM | VK | IeM | TM | KEM |  |  |  | SM plāns | SM izpilde | EM plāns | EM izpilde | VARAM plāns | VARAM izpilde | IZM plāns | IZM izpilde | VM plāns | VM izpilde | LM plāns | LM izpilde | KM plāns | KM izpilde | FM plāns | FM izpilde | VK plāns | VK izpilde | IeM plāns | IeM izpilde | TM plāns | TM izpilde | KEM plāns | KEM izpilde
2022 IV | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! |  |  | 2022 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 2023 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 103.8547 | 4.35 | 2023 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Uzsaukums par elastības finansējuma apjomu 2026.g. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Uzsaukums par elastības finansējuma apjomu 2026.g. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
BEZ KUMULATĀCIJAS
Laika grafiks uz 25.04.2023.
| MK noteikumu finansējums pa ministrijām kumulatīvi, milj. EUR | [25 empty] | MK noteikumu finansējums pa ministrijām uz 25.04.2023., milj. EUR
| SM | NOBĪDE | EM | NOBĪDE | VARAM | NOBĪDE | IZM | NOBĪDE | VM | NOBĪDE | LM | NOBĪDE | KM | NOBĪDE | FM | NOBĪDE | VK | NOBĪDE | IeM | NOBĪDE | TM | NOBĪDE | KEM | NOBĪDE |  |  |  | SM | EM | VARAM | IZM | VM | LM | KM | FM | VK | IeM | TM | KEM
2022 IV | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! |  |  | 2022 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Uzsaukums par elastības finansējuma apjomu 2026.g. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Uzsaukums par elastības finansējuma apjomu 2026.g. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Kopā | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
KUMULATĪVI
Laika grafiks uz 25.04.2023.
| Projektu atlases pa ministrijām kumulatīvi, milj. EUR | [14 empty] | Projektu atlases kumulatīvi uz 25.04.2023., milj. EUR | [14 empty] | KM: Sākotnēji plānotie grafiki 30.09.2022.
| SM | EM | VARAM | IZM | VM | LM | KM | FM | VK | IeM | TM | KEM |  |  |  | SM | EM | VARAM | IZM | VM | LM | KM | FM | VK | IeM | TM | KEM | [6 empty] | MK noteikumu finansējums pa ministrijām kumulatīvi uz 30.09.2023., milj. EUR
2022 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2022 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | EM | VM | IeM | KEM | IZM | VARAM | TM
2023 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | 2022 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | MK noteikumu skaits
2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | EM | VM | IeM | KEM | IZM | VARAM | TM
2024 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | 8 | 3 | 1 | 1 | 2 | 1 | 1
2024 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Uzsaukums par elastības finansējuma apjomu 2026.g. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Uzsaukums par elastības finansējuma apjomu 2026.g. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
BEZ KUMULATĀCIJAS
Laika grafiks uz 25.04.2023.
| Projektu atlases pa ministrijām kumulatīvi, milj. EUR | [14 empty] | Projektu atlases kumulatīvi uz 25.04.2023., milj. EUR
| SM | EM | VARAM | IZM | VM | LM | KM | FM | VK | IeM | TM | KEM |  |  |  | SM | EM | VARAM | IZM | VM | LM | KM | FM | VK | IeM | TM | KEM
2022 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2022 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2023 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2024 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2024 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2025 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2025 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Uzsaukums par elastības finansējuma apjomu 2026.g. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Uzsaukums par elastības finansējuma apjomu 2026.g. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2026 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2026 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 II | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 III | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2027 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 2027 IV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | EM | VARAM | IZM: IZM; VM: IeM; LM: SM
| Projektu atlases izpilde uz 2023.g. I cet. pa ministrijām, milj. EUR | 0 | #REF! | IZM: 0; VM: 0; LM: 0
| Projektu atlases plāns 2023.g. I cet. pa ministrijām, milj. EUR | #REF! | #REF! | IZM: 0; VM: #REF!; LM: 0
| MK noteikumu apstiprināšanas izpilde uz 2023.g. I cet. pa ministrijām, milj. EUR | 0 | #REF! | IZM: 0; VM: 0; LM: 0
| MK noteikumu apstiprināšanas plāns 2023.g. I cet. pa ministrijām, milj. EUR | #REF! | #REF! | IZM: #REF!; VM: #REF!; LM: #REF!
Būvniecības PPT 0906.2023
|  | Atlašu plānotais kopējais finansējums milj. EUR | Atlašu plānotais skaits
| 2023.g II cet | 14.6391 | 1
| 2023.g III cet | 866.8024 | 9
| 2023.g IV cet | 748.301 | 19
| 2024.g I cet | 606.0958 | 16
| 2024.g II cet | 553.8431 | 14
| 2024.g III cet | 86.9908 | 7
| 2024.g IV cet | 60.3878 | 3
| 2025.g I cet | 82.0178 | 3
| 2026.g I cet | 32.0425 | 1 | [26 empty] | MK noteikumu skaits
[30 empty] | SM | EM | VARAM | IZM | VM | LM | KM | FM | VK | IeM | TM | KEM
[30 empty] | 9 | 19 | 20 | 33 | 11 | 19 | 5 | 2 | 6 | 3 | 3 | 1
3B ppt grafikam | [10 empty] | EM | VARAM | IZM | IeM | SM | KEM | VM | LM | TM | VK
Year and Quarter | Cabinet of Ministers rules for SO/ measure implementation, cumulatively mil. EUR | Calls of project selection, cumulatively mil. EUR | Number of calls for project selection | Number of calls for project selection, cumulatively | [5 empty] | Projektu atlases izpilde uz 2023.g. I cet. pa ministrijām, milj. EUR | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023 I | #REF! | #REF! | 1 | 1 | [5 empty] | Projektu atlases plāns 2023.g. I cet. kumulatīvi pa ministrijām, milj. EUR | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 II | #REF! | #REF! | 8 | 9 | [5 empty] | MK noteikumu apstiprināšanas izpilde uz 2023.g. I cet. pa ministrijām, milj. EUR | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023 III | #REF! | #REF! | 26 | 35 | [5 empty] | MK noteikumu apstiprināšanas plāns 2023.g. I cet. kumulatīvi pa ministrijām, milj. EUR | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2023 IV | #REF! | #REF! | 55 | 90
2024 I | #REF! | #REF! | 43 | 133
2024 II | #REF! | #REF! | 22 | 155
2024 III | #REF! | #REF! | 15 | 170
2024 IV | #REF! | #REF! | 4 | 174
2025 I | #REF! | #REF! | 3 | 177
2025 II | #REF! | #REF! | 1 | 178
2025 III | #REF! | #REF! | 0 | 178
2025 IV | #REF! | #REF! | 0 | 178
2026 I | #REF! | #REF! | 2 | 180
Flexibility amount in 2026 | #REF! | #REF! | 5 | 185
2026 II | #REF! | #REF! | 0 | 185
2026 III | #REF! | #REF! | 0 | 185
2026 IV | #REF! | #REF! | 0 | 185
2027 I | #REF! | #REF! | 0 | 185
2027 II | #REF! | #REF! | 0 | 185
2027 III | #REF! | #REF! | 0 | 185
2027 IV | #REF! | #REF! | 1 | 186
3B ppt rimbuļi
| Cabinet of Ministers rules to be adopted in 2023 | #REF!
| Cabinet of Ministers rules to be adopted later | #REF!
| Calls of project selection in 2023 | #REF!
| Calls of project selection in next years | #REF!
[12 empty] | SM | IZM | EM | VARAM | VM | LM | KM | FM | VK | IeM | KEM | TM
[11 empty] | Plāns 2023.g. pa ministrijām, milj. EUR | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[11 empty] | Izpilde uz 27.06.2023 pa ministrijām, milj. EUR |  |  |  | #REF! | LM: 4.35